## Sheet1
Action Number | Title | Current Status | Status | Action Owner | Origin in Agenda / Minutes | Notes
202301 | Action List | Maintain list of actions and their status 15/6/23 This document is it! | Complete | Council Officers |  | this is it
202302 | Internal Audit report |  |  | Council Officers | 2023-05-23 FinC minute 23.03.10
202303 | Internal Audit report | Ask the Internal Auditor if they have a sample financial control checklist | Complete | Council Officers | 2023-05-23 FinC minute 23.03.10.1 | Have document
202304 | Internal Audit report | Look at risk management assessment in light of inflation etc, Joint Panel on Accountability and Governance (JPAG) Society of Local Council Clerks (SLCC) Budgetary control were done and will continue to do so | Ongoing | Members | 2023-05-23 FinC minute 23.03.10,2
202305 | Internal Audit report | Investigate insurance minimum requirements regarding valuations or level of cover, to be approved at Full Council | Ongoing | Council Officers | 2023-05-23 FinC minute 23.03.10.3 | Final of 3 quotes received.
202306 | Asset Register | Compare version at July meeting to Excel register | Ongoing | CR | Jul 2023 FinC meeting
202307 | Internal Audit report | JE investment register & strategy | Ongoing | JE | 2023-05-23 FinC minute 23.03.10.5 | not started & see 202327
202308 | Internal Audit report | Monitor website | Ongoing | JE | 2023-05-23 FinC minute 23.03.10.6 | started
202310 | Internal Audit report | Review the effectiveness of Internal Audit document and bring to the next meeting for approval. | Complete | Members | 2023-05-23 FinC minute 23.03.10.8 | capproved 13/6/23
202311 | Asset Register | Check updated Asset Register | Ongoing | Members | 2023-05-23 FinC minute 23.03.11
202312 | Asset Register | Update Scribe - add date of acquisition. | Ongoing | Council officers | 2023-05-23 FinC minute 23.03.11.1
202313 | Asset Register | old items need to come off & revisit the list to get breakdown on the historic £5k line | Ongoing | Council Officers | 2023-05-23 FinC minute 23.03.11,2
202314 | Asset Register | continue existing policy of adding new items at cost and remove items disposed of. | Complete | Council Officers | 2023-05-23 FinC minute 23.03.11.3 | part of update
202315 | Asset Register | Breakdown into a list of items held at nominal value and others. | Ongoing | Council Officers | 2023-05-23 FinC minute 23.03.11.4 | not yet ready
202317 | Asset Register | check Sheepcot gates are not duplicated, | Ongoing | Council Officers | 2023-05-23 FinC minute 23.03.11.6 | which gates?
202318 | Asset Register | check Gardiner gates - if donated have no value. | Ongoing | Council Officers | 2023-05-23 FinC minute 23.03.11.7 | confirm donated by TBD
202319 | Asset Register | Salt & grit bins – are they GPC.? | Complete | Council Officers | 2023-05-23 FinC minute 23.03.11.8 | They are OCCs
202321 | CIL records | Officers of the Council to maintain a spreadsheet showing CIL receipts and remaining balances where partially spent. When there is a change provide updates sheet to next FC meeting. . | Complete | Council Officers | 2023-05-23 FinC minute 23.03.12.2 8/6/23 Agenda item 8 | Updated
202322 | Grants policy | Check that renewing Grants Policy will not stop us receiving grants from major potential donors. eg SODC (as MFR) / OCC (ask at OCC course, ask Kevin Bumer) / others? | Ongoing | Members | 2023-05-23 FinC minute 23.03.12.3 8/6/23 Agenda item 8 | JE and AS to meet with SODC. JE to contact Kbulmer.
202323 | TSB Bank access | Setup TSB account access for FinC to approve payment | Ongoing | Council Officers | 2023-05-23 FinC minute 23.03.12.4 | 24.7.23 TSB Mandate to be sent to add CR and remove BU, once completed, the rest of the FinC will be added.
202324 | Budget movements | Consideration of budget and any movements as a regular monthly agenda item | Ongoing | Council Officers | 2023-06-13 FinC agenda item 9 | to be on August agenda
202325 | Grant for LED street lights | Look into grants for converting streetlights to LEDs (greening) eg TOE / Mend the Gap / Information on DoE website | Ongoing | Council Officers | 2023-06-13 FinC agenda item 9 | Andy & Jim to enquire at SODC
202326 | Funding for LED street lights | Confirm that CIL can be used | Complete | Council Officers | 2023-06-13 FinC agenda item 9 | it can
202327 | Savings/Investment Account for reserves | Investigate potential investment accounts for up to £85k (each) eg CCLA Public sector deposit Fund / Unity Trust saving Account / Redwood Bank / Hampshire Trust/Metro/Black Rock/Lloyds/Cambridge | Ongoing | JE | 2023-06-13 FinC agenda item 9 | not started
202328 | CIL balance | £1,000 difference to be explained or reconciled. ( exactly £1k discrepancy in two calcualtions of CIL total - probably keying in error in one) | Ongoing | Council Officers | 2023-07-11 FinC minute 23.12.8.1
202329 | EMR movements | Need to ipdate with payments made for streetlight replacemtn lanterns | Ongoing | Council Officers | 2023-07-11 FinC minute 23.12.9.1
202330 | EMR movements | Check if Sheepcot grass mats & Jubille garden maintenece are recorde as per approved budget spend | Ongoing | Council Officers | 2023-07-11 FinC minute 23.12.9.2
202331 | Qtly report to Council | Prepare budget report at at 31 July for August Finance meeting to check spending is on track. Use result for 'quarterly' review to September Full Council | Ongoing | Council Officers | 2023-07-11 FinC minute 23.12.10.1