## Sheet1
Action Number | Title | Current Status | Action Owner | Status
2021-001 | High Street No Loading / No Waiting Zone | Officers of the Council to monitor issues with parking and loading on the High Street, to bring back to the Committee if problem continues. 23 May 2023 - Letter sent & SL and DB have visited - no response to date. To seek contact details for the manager. 20 June 2023 - A councillor has sought to get these, but was unable to. The new owners continue to park on the shop frontage, and on the public highway. Action to seek contact details of Licencee (LW). 15 August 2023 - Ongoing- find out the licencee details. 17 October 2023 - Telephone contact for owner/manager obtained, contact to be made. | Council Officers & SL | Monitoring
2021-002 | Speed Bumps at the end of Elvendon Road | Officers of the Council to monitor issues with parking and loading on the High Street, to bring back to the Committee if problem continues. 23 May 2023 - Letter sent & SL and DB have visited - no response to date. To seek contact details for the manager. 20 June 2023 - A councillor has sought to get these, but was unable to. The new owners continue to park on the shop frontage, and on the public highway. Action to seek contact details of Licencee (LW). 15 August 2023 - Ongoing- find out the licencee details |  | Closed.
2021-003 | Junction of Yew Tree Court and Station Road | Officers of the Council to monitor issues with parking and loading on the High Street, to bring back to the Committee if problem continues. 23 May 2023 - Letter sent & SL and DB have visited - no response to date. To seek contact details for the manager. 20 June 2023 - A councillor has sought to get these, but was unable to. The new owners continue to park on the shop frontage, and on the public highway. Action to seek contact details of Licencee (LW). 15 August 2023 - Ongoing- find out the licencee details | N/A | Closed
2021-004 | Station Road Pedestrian Safety | Subsequent to informal public consultation, approved to pursue trial pedestrian priority lane with 18month TTRO to suspend the parking bays. 18 July 2023 - No Update, awaiting Consultation - in late summer / early autumn. [NOTE] One consultation with yellow line reveiw - to be repainted after consultation WITH the painting at Sheepcot - PPL in entrance road and all the spaces repainted. 15 August 2023 - No Update. 12 September 2023 - Have e-mailed OCCH - asking for update on consultation, response from OCCH - unlikely to consult before Christmas. 17 October 2023 - Chair e-mailed Cllr K Bulmer OCC for update. | OCC Highways | Monitoring / Awaiting Implementation
2021-005 | 20mph Application | Applied for, awaiting OCCH update on progress 21 Feb 2023 - Confirmed Approved, awaiting start date. 21 Mar 2023 - Implemented - Close Item. | OCC Highways | Closed.
2022-001 | Rectory Garden Verge Planting | 21 Feb 2023 - No Update, Monitoring levels of parking. | Committee | Monitoring / On Hold.
2022-002 | Additional High Street Traffic Calming | A crossing hump at near Red Cross Road Junction and Mini Roundabout a the Junction of Manor Road and High Street were both originally proposed. Mini Roundabout it not possible. To pursue speed hump between Social Club and Junction with Red Cross Road, as part of whole village safety assessment. | Committee | Closed / See 2022-015
2022-003 | Whole Village Yellow Lines Review | To complete full review, include in whole village safety assessment. ACTION August 2022 meeting: All committee members to meet informally and review. | Committee | Closed / See 2022-015
2022-004 | Civil Parking Enforcement | To investigate options pertaining to a shared parking enforcement officer with other local parishes. OCC is against the principle of a single parish enforcement officer & Include | BU | Closed / See 2022-015
2022-005 | Junction of Red Cross Road and Station Road & other Bollards | 13 Dec 2022 - Was meant to be installed 30th Nov - Not installed yet - to contact OCCH again. 17 Jan 2023 - Rescheduled for installation on the 16th January - to contact OCCH again. 21 Feb 2023 - Awaiting new installation date for bollard outside Bridal Shop, and to chase the "bouncy" boilards, 2 on High St build out and 2 on Cleeve Road opposite Gardiner. 21 Mar 2023 - Installed - Closed Item | OCC Highways | Closed.
2022-006 | High Street Drains | OCCH had asked GPC to rod the drains on either side of the speed hump. GPC reminded OCC drains were their responsibility. Council Officers asked to remind OCCH of their responsibility and ask that it be done before the winter. 18 Oct 2022 - To ask OCCH for update, plus inform OCCH the non slip coating has degraded over the drain. 15 Nov 2022 - To include in letter to OCCH e-mail sent 15th Nov 2022 13 Dec 2022 - Meant to be completed by now - if flooding happending to raise on Fix My Street again - similarly for drain coating. | Council Officers | Closed
2022-007 | Flashing Speed Indicator Signs | 23 May 2023 - 20mph now enforcable. Plan to be prepared for the next meeting. - To check the 30mph sign before the flashing dots - toward Wallingford. 20 June 2023 - Plan presented at meeting, and attached to these minutes. 18 July 2023 - Plan is Appendix A to 20th June meeting - has been sent to OCCH for consideration. 19 September 2023 - Main Agenda Item, so seek Council approval and to proceed. 20 September 2023 - OCCH advise that it is possible to connect a power supply from the main cable to a post on the Reading Rd, adjacent to the Burial Ground the cost would be met by OCCH, the cost of signs and electricty would be met by GPC. 17 October 2023 - Main Agenda item. | Committee / Full Council Delegation Request | Open
2022-008 | Additional Speed Surveys | 24 May 2023 - 20mph now enforcable. Plan to be prepared for the next meeting. - To check the 30mph sign before the flashing dots - toward Wallingford. 20 June 2023 - Plan presented at meeting, and attached to these minutes. 18 July 2023 - Plan is Appendix A to 20th June meeting - has been sent to OCCH for consideration. 19 September 2023 - Main Agenda Item, so seek Council approval and to proceed. 20 September 2023 - OCCH advise that it is possible to connect a power supply from the main cable to a post on the Reading Rd, adjacent to the Burial Ground the cost would be met by OCCH, the codt of signs and electricty would be met by GPC. | Committee | Closed
2022-009 | Dropped Kerb Survey | 25 May 2023 - 20mph now enforcable. Plan to be prepared for the next meeting. - To check the 30mph sign before the flashing dots - toward Wallingford. 20 June 2023 - Plan presented at meeting, and attached to these minutes. 18 July 2023 - Plan is Appendix A to 20th June meeting - has been sent to OCCH for consideration. 19 September 2023 - Main Agenda Item, so seek Council approval and to proceed. 20 September 2023 - OCCH advise that it is possible to connect a power supply from the main cable to a post on the Reading Rd, adjacent to the Burial Ground the cost would be met by OCCH, the codt of signs and electricty would be met by GPC. | Committee | Closed / See 2022-015
2022-010 | Overgrown Hedges | 18 July 2023 - Ongoing + add letter to house in North West Corner of the railway bridge, Mill Road. Resend letters to Gatehamptom Road Early September - after nesting season. 15 August 2023 - Hedge Letters sent, Lockstile Mead, Elvendon Road. Still to send: North West Corner of the railway bridge, Mill Road. Resend letters to Gatehamptom Road Early September - after nesting season (Clerk team to monitor and report progress). Check hedges on the Red Cross Road/High St/Upper Red Cross Road Junction. Check the footpath from Holmlea to Platform 1 (W3W freshen.twinkled.confining) 19 September 2023 - Assistant Clerk to review all previous hedge letters, send reminders new letters. | Council Officers | Ongoing NB consider enforcement after the nesting season for any untrimmed hedges.
2022-011 | London Plane Tree @ Bridge House | A number of optins have been considered, including adding pedestrian crossing, swept kerb etc. The tree is protected and cannot be cut. Any solution will be very costly. This is not a PC Tree, the Highway is the responsibility of OCC. Action Closed, this Committee does not have the resoure or powers do anything usefully to resolve this. ACTION: Council Officers to Write to Piereponts to ask for a clearly defined pedestrian path. ACTION: Committee member to update home owner. 15 Nov 2022: Ongoing 13 Dec 2022 - CLOSED | Council Officers and Committee Members | Closed.
2022-012 | Parking at the Railway Cottages | To continue to investigate possible Actions 15 Nov 2022: Ongoing 13 Dec 2022 - to be included as part of whole village parking review - potential for permit parking - Assistant Clerk to assertain who owns the road itself. | LW | Closed - Move to 2022-015
2022-013 | Provision of EV Parking Spaces | 20 June 2023 - SSE and Enerveo contacted, would need to take the columns out of the current agreement of unmetered electricity. SSE recommended contacting ubitricity, which has been done. SODC have also confirmed Wheel Orchard Car Park is also being considered for chargers, but number and when is yet to be decided. Assistant Clerk to following up with MH @ OCCH re EV charging bay and getting the EV bay on the autumn consulatation. 18 July 2023 - Assistant Clerk has been in conversation with SODC and OCC EV teams - they are specifically looking for spaces where there is limited ability for residents to have home chargers. Email has been sent back of location etc, but no further response from EV team. [ACTION] to email SODC EV Team about the 2 "odd spaces" in the wheel orchard car park. 15th August 2023 - Assistant Clerk has completed an expression of interest for Community Centre, and Glebe Ride Street almps with OCC on their new grant scheme opportunity for Electric Vehicle chargers. 19th September 2023 - No Update, "the two odd spaces was detailed on the expression of interest form." 17 October 2023 - Two spaces in Wheel Orchard carpark appear to be listed by OCCH, chargers on lampposts in Glebe Rise to be considered in demand mapping, position appears substantially as at August. | Committee | Open / See 2022-015 Assistant Clerk
2022-014 | Pedestrians Crossing Gatehampton Road, near Station | 21 Mar 2023 - LW to talk to station manager. Consider a white line crossing zone rather than a zebra crossing, to mark a safe area to cross, and ask if the far end of the car parking area be restored from existing use as storage area? 23 May 2023 - e-mail sent - no response yet. 18 July 2023 - LW to contact additional contact details given by a member of public - Ongoing 15 August 2023 - Network Rail were the INCORRECT people to contact, to chase the station manager again. Clerk to make contact. 17 October - No Progress. | Council Officers | Open
2022-015 | Full Village Pedestrian Safety Review | 23 May 2023 - Speed Hump: OCC would consider as a 2024 project to appropriate scheme - propose Ganville engaged. Additional Line Painting drawing provided to OCC. All street lights to be inventoried and numbers checked - All councillors to help. Raiway cottages - no further update, all quiet - propose Close unless they get in touch again. LW to ask Glanville for a price to come up with the scheme. 18 July 2023 - Glanvilles Contacted for quote - full details to be presented at the meeting. £9k for Glanvilles Scheme and OCC formal consultation to the public + build costs. SL to ask OCCH indicative installation costs. [ACTION] To publicise everywhere Civil Parking Enforcement (CPE) reporting form which is on OCC website. 17 October 2023 - Main Agenda Item. | Committee | Open
2022-016 | Parking on Pavements | To check status of law, progress etc. 15 Nov 2022: Ongoing. 13 Dec 2022 - no current update to the law, on going - CLOSED. | Council Officers | Closed.
2022-017 | Manor Road | Endeavour to monitor the construction plan for the GNP3 site. 23 May 2023 - To ask if the Yellow lines need to be reinstated where the development is. 20 June 2023 - Line will be repainted by the developer, OCCH Yellow Line expert to assess next time in Goring. LW to find out more about connecting the newly re-found gully to the drainage. 18 July 2023 - Confirmed not intended to be connected, this area is meant to drain in to the verges. | Councillors - RW | Closed
2023-001 | Gigaclear | 23 May 2023 - a watch item to keep aware of any issues with the installation and reinstatement of the highways. Cllr JH will attend the open Gigaclear session in Goring on Thursday 25th May. LW - to ensure contact details for concerns are on the GPC website. 20 June 2023 - Confirmed 18 July 2023 - JH To attend Zoom on Gigaclear Feedback 21/07/2023 15 August 2023 - Update from JH - fibre is being installed in the ducting, no end date. The gigahub is live in Heron Shaw. The digging is complete, continue monitoring of the repairs. 17 October 2023 - No Update | MH & JH | Open
2023-002 | Thames Water works on Manor Road. | 15 August 2023 - Clerk team to write to Thames Water re: speeds of operatives, particularly on Manor Road. 17 October 2023 - No Update. | MH | Open
2023-003 | Access to Sheepcote | 17 October 2023 (Item transferred from 2021-004). Painting of PPL in entrance road and all the parking spaces repainted to be done in conjunction with painting of PPL in Station Rd. | MH | Open